## Group Leader To-do List
To-do list
To be completed by: |  | 2025-12-16 |  | Name: Theophilus Bassaw
Deadline: |  | 2025-12-16 |  | Date: 12/16/2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-07 | 2025-12-14 | 2025-12-16 | 9 | Was given an extension
100% | Working on tvfs and Stored Procedures | 2025-12-07 | 2025-12-14 | 2025-12-16 | 9 | Was given an extension
100% | Putting together code contributations and looked over work | 2025-12-07 | 2025-12-14 | 2025-12-16 | 9 | Was given an extension
100% | Prepare Git repository for submittion | 2025-12-16 | 2025-12-14 | 2025-12-16 | 1 | Was given an extension
100% | Prepare Todo list and Gannt Chart | 2025-12-16 | 2025-12-14 | 2025-12-16 | 1 | Was given an extension
100% | Record presentation and upload to Youtube | 2025-12-16 | 2025-12-14 | 2025-12-16 | 1 | Was given an extension
100% | Generate Database Backup and .sql files | 2025-12-16 | 2025-12-14 | 2025-12-16 | 1 | Was given an extension

## Group Leader Gannt Chart
PROJECT # 4
Theophilus Bassaw
|  |  |  | week of 11/30 | week of 12/7 | [6 empty] | week of 12/14
|  |  |  | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT | SUN | MON | TUE
Working on Table Code | 2025-12-07 | 9 | 2025-12-16 | bar: week of 12/7 7 SUN to week of 12/14 10 WED
Working on tvfs and Stored Procedures | 2025-12-07 | 9 | 2025-12-16 | bar: week of 12/7 7 SUN to week of 12/14 10 WED
Putting together code contributations and looked over work | 2025-12-07 | 9 | 2025-12-16 | bar: week of 12/7 7 SUN to week of 12/14 10 WED
Prepare Git repository for submittion | 2025-12-16 | 1 | 2025-12-16
Prepare Todo list and Gannt Chart | 2025-12-16 | 1 | 2025-12-16
Record presentation and upload to Youtube | 2025-12-16 | 1 | 2025-12-16
Generate Database Backup and .sql files | 2025-12-16 | 1 | 2025-12-16

## Jacelin Gomez To-do List
To-do list
To be completed by: |  | 2025-12-16 |  | Name: Jacelin Gomez
Deadline: |  | 2025-12-16 |  | Date: 12/16/2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-10 | 2025-12-14 | 2025-12-16 | 7
100% | Working on Presentation | 2025-12-10 | 2025-12-14 | 2025-12-16 | 7
0% | Working on Proposition | 2025-12-12 | 2025-12-14 | 2025-12-16 | 5
100% | Sending Scripts to Theo | 2025-12-12 | 2025-12-14 | 2025-12-16 | 5

## Jacelin Gomez Gannt Chart
PROJECT #4
Jacelin Gomez
[10 empty] | Week of 12/7 | [6 empty] | Week of 12/14
|  |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THUR | FRI | SAT
Working on Table Code | 2025-12-10 | 5 | 2025-12-14 | bar: 10 WED to Week of 12/7 14 SUN
Working on Presentation | 2025-12-10 | 7 | 2025-12-16 | bar: 10 WED to Week of 12/7 16 TUE
Working on Proposition | 2025-12-12 | 5 | 2025-12-16 | bar: 12 FRI to Week of 12/7 16 TUE
Sending Scripts to Theo | 2025-12-12 | 5 | 2025-12-16 | bar: 12 FRI to Week of 12/7 16 TUE

## Mateo Chimbo To Do List
To-do list
To be completed by: |  | 2025-12-16 |  | Mateo Chimbo
Deadline: |  | 2025-12-16 |  | Date: 16-Dec-25
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-10 | 2025-12-14 | 2025-12-16 | 5
80% | Working on Presentation | 2025-12-10 | 2025-12-14 | 2025-12-16 | 7
70% | Working on Proposition | 2025-12-10 | 2025-12-14 | 2025-12-16 | 7
100% | Sending Scripts to Theo | 2025-12-10 | 2025-12-14 | 2025-12-16 | 5

## Mateo Chimbo Gannt Chart
PROJECT #4
Mateo Chimbo
|  |  |  | week of 11/30 | week of 12/7 | [6 empty] | week of 12/14
|  |  |  | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT | SUN | MON | TUE
Working on Table Code | 2025-12-10 | 5 | 2025-12-14 | bar: week of 12/14 10 WED
Working on Presentation | 2025-12-10 | 7 | 2025-12-16 | bar: week of 12/14 10 WED
Working on Proposition | 2025-12-10 | 7 | 2025-12-16 | bar: week of 12/14 10 WED
Sending Scripts to Theo | 2025-12-10 | 5 | 2025-12-14 | bar: week of 12/14 10 WED

## Rahat Moktadir To Do List
To-do list
To be completed by: |  | 2025-12-16 |  | Name: Rahat Moktadir
Deadline: |  | 2025-12-16 |  | Date: 12/16/2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-10 | 2025-12-14 | 2025-12-16 | 7 | Was given an extension
80% | Working on Presentation | 2025-12-10 | 2025-12-14 | 2025-12-16 | 7 | Was given an extension
30% | Working on Proposition | 2025-12-13 | 2025-12-14 | 2025-12-16 | 4 | Was given an extension
100% | Sending Scripts to Theo | 2025-12-13 | 2025-12-14 | 2025-12-16 | 4 | Was given an extension

## Rahat Moktadir Gannt Chart
PROJECT 4
Rahat Moktadir
|  |  |  | week of 11/30 | week of 12/7 | [6 empty] | week of 12/14
|  |  |  | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT | SUN | MON | TUE
Working on Table Code | 2025-12-10 | 7 | 2025-12-16 | bar: week of 12/14 10 WED
Working on Presentation | 2025-12-10 | 7 | 2025-12-16 | bar: week of 12/14 10 WED
Working on Proposition | 2025-12-13 | 4 | 2025-12-16
Sending Scripts to Theo | 2025-12-13 | 4 | 2025-12-16

## Unsa Chaudhry To Do List
To-do list
To be completed by: |  | 2025-12-16 |  | Unsa Chaudhry
Deadline: |  | 2025-12-16 |  | Date: 12/16/2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-10 | 2025-12-14 | 2025-12-15 | 5
100% | Working on Presentation | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2
100% | Working on Proposition | 2025-12-10 | 2025-12-14 | 2025-12-15 | 5
100% | Sending Scripts to Theo | 2025-12-10 | 2025-12-14 | 2025-12-15 | 5

## Unsa Chaudhry Gannt Chart
PROJECT 4
Unsa Chaudhry
|  |  |  | week of 11/30 | week of 12/7 | [6 empty] | week of 12/14
|  |  |  | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT | SUN | MON | TUE
Working on Table Code | 2025-12-10 | 5 | 2025-12-15 | bar: week of 12/14 10 WED
Working on Presentation | 2025-12-13 | 2 | 2025-12-15
Working on Proposition | 2025-12-10 | 5 | 2025-12-15 | bar: week of 12/14 10 WED
Sending Scripts to Theo | 2025-12-10 | 5 | 2025-12-15 | bar: week of 12/14 10 WED

## Prachi Purkaystha To Do List
To-do list
To be completed by: |  | 2025-12-16 |  | Name: Prachi Purkaystha
Deadline: |  | 2025-12-16 |  | Date: 12/16/2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-10 | 2025-12-16 |  | 5 | Created BuildingLocation and Room tables, added PK/FK constraints, populated data, and validated joins with course offerings
80% | Working on Presentation | 2025-12-15 | 2025-12-16 | 2025-12-16 | 1 | Prepared explanation of normalization, schema design, and join results for presentation slides
90% | Working on Proposition | 2025-12-15 | 2025-12-16 |  | 1 | Defined problem, normalization approach, and justification for splitting Location into Building and Room entities
100% | Sending Scripts to Theo | 2025-12-15 | 2025-12-16 |  | 1 | Sent SQL scripts, screenshots of tables, and join query results to group leader for integration

## Prachi Purkaystha Gannt Chart
PROJECT # 4
Prachi Purkaystha
|  |  |  | week of 11/30 | week of 12/7 | [6 empty] | week of 12/14
|  |  |  | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT | SUN | MON | TUE
Working on Table Code | 2025-12-10 | 5 | 2025-12-15
Working on Presentation | 2025-12-15 | 1 | 2025-12-16
Working on Proposition | 2025-12-15 | 1 | 2025-12-16
Sending Scripts to Theo | 2025-12-15 | 1 | 2025-12-16

## Sameeha Kamal To Do List
To-do list
To be completed by: |  | 2025-12-16 |  | Sameeha Kamal
Deadline: |  | 2025-12-16 |  | Date: 12/16/2025
Project 4
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Working on Table Code | 2025-12-10 | 2025-12-14 | 2025-12-16 | 6 | Finalize normalization, constraints, and UDT validation
80% | Working on Presentation | 2025-12-14 | 2025-12-14 | 2025-12-16 | 2 | Revised to align slide structure with rubric and add ERD/EDM screenshots
100% | Working on Proposition | 2025-12-12 | 2025-12-14 | 2025-12-16 | 4 | Additional time needed to validate query logic and outputs.
100% | Sending Scripts to Theo | 2025-12-12 | 2025-12-14 | 2025-12-16 | 4 | Delayed due to final SQL clean up and consistency checks

## Sameeha Kamal Gannt Chart
PROJECT 4
Sameeha Kamal
|  |  |  | week of 12/7 | week of 12/14
|  |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Task | Start Date | Days Needed | Completion Date | SUN | MON | TUE | WED | THU | FRI | Sat | SUN | MON | TUE | WED | THUR | FRI | SAT
Working on Table Code | bar: week of 12/14 10 WED to week of 12/14 16 TUE
Working on Presentation | bar: week of 12/14 14 SUN to week of 12/14 16 TUE
Working on Proposition | bar: week of 12/14 12 FRI to week of 12/14 16 TUE
Sending Scripts to Theo | bar: week of 12/14 12 FRI to week of 12/14 16 TUE